## Summary
Leave Forms Revamp — Progress Checklist
Scored against Laravel API · docs/SCHEMA.md, BALANCE_FLOW.md, APPROVAL_RULES.md, LEGACY_NOTES.md · Updated 2026-07-22
React frontend is a separate repo and is not scored here. Partial = 50% of a task. Recent: submit + confirm email notifications.
Overall % | 57%
Tasks Done | 51 | Partial | 2 | Todo | 38
Section | Modules | Tasks | Done | Partial | Todo | Progress %
Foundation | 2 | 11 | 9 | 0 | 2 | 82%
Employee Leave Filing | 4 | 26 | 22 | 0 | 4 | 85%
Approver / PIC | 2 | 16 | 10 | 1 | 5 | 66%
Balance & Credits | 2 | 15 | 6 | 0 | 9 | 40%
Admin / Special Flows | 4 | 23 | 4 | 1 | 18 | 20%
Module breakdown
Section | Module | Tasks | Done | Partial | Todo | Progress %
Foundation | Schema & Data Model | 5 | 5 | 0 | 0 | 100%
Foundation | Portal Auth & Access | 6 | 4 | 0 | 2 | 67%
Employee Leave Filing | Submit Leave (VL) | 11 | 10 | 0 | 1 | 91%
Employee Leave Filing | My Leaves List | 4 | 3 | 0 | 1 | 75%
Employee Leave Filing | Modify Leave (while pending) | 6 | 5 | 0 | 1 | 83%
Employee Leave Filing | Cancel Leave | 5 | 4 | 0 | 1 | 80%
Approver / PIC | Pending Approvals Dashboard | 5 | 3 | 0 | 2 | 60%
Approver / PIC | Approve / Reject Leave | 11 | 7 | 1 | 3 | 68%
Balance & Credits | Balance Ledger & Buckets | 9 | 4 | 0 | 5 | 44%
Balance & Credits | Legacy Balance Migration | 6 | 2 | 0 | 4 | 33%
Admin / Special Flows | VL → SL Conversion | 7 | 1 | 0 | 6 | 14%
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | 5 | 1 | 0 | 4 | 20%
Admin / Special Flows | Reports & Visibility | 5 | 0 | 1 | 4 | 10%
Admin / Special Flows | Notifications (remaining) | 6 | 2 | 0 | 4 | 33%
Suggested next priorities
1. Reject notification email (+ optionally notify next-tier approvers after partial approve)
2. VL → SL conversion APIs + admin review + balance side effects
3. Annual entitlement + monthly accrual jobs
4. Feature tests for submit → approve → confirm happy path
5. Stakeholder answers for other leave types + report access
6. Production balance migration script from leave_confirmation

## Checklist
Leave Forms Revamp — Module / Task Checklist
Updated 2026-07-22 · Status: Done / Partial / Todo · Module % uses Partial = 0.5
Section | Module | Task | Status | Module % | Notes
Foundation | Schema & Data Model | Migrations — 8 revamp tables (leave_type → leave_conversion) | Done | 100% | migrations present
Foundation | Schema & Data Model | Indexes & unique constraints (SCHEMA.md) | Done | 100%
Foundation | Schema & Data Model | Eloquent models + PHP backed enums | Done | 100%
Foundation | Schema & Data Model | LeaveTypeSeeder (VL, SL, EL, ML, PL, PTB, LL) | Done | 100%
Foundation | Schema & Data Model | kdtphdb read models (employee, formspic, holiday, login) | Done | 100%
Foundation | Portal Auth & Access | Dual DB setup — formsdb + kdtphdb (read-only) | Done | 67%
Foundation | Portal Auth & Access | Portal cookie auth (userID → kdtlogin) | Done | 67%
Foundation | Portal Auth & Access | Routes — GET /api/me, GET /api/health | Done | 67%
Foundation | Portal Auth & Access | Config — president_emp_id, CORS, attachments, notifications | Done | 67%
Foundation | Portal Auth & Access | Production portal / session cutover with infra | Todo | 67% | LEGACY_NOTES open item
Foundation | Portal Auth & Access | Testing — auth middleware & health checks | Todo | 67%
Employee Leave Filing | Submit Leave (VL) | Routes & controller — POST /leaves | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Validation — StoreLeaveRequest + attachment rules | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Duration calc — workdays, holidays, half-day | Done | 91%
Employee Leave Filing | Submit Leave (VL) | paid_days / lwop_days split from available | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Snapshot approval requirements at submit | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Reserve paid credits (leave_reserved) | Done | 91%
Employee Leave Filing | Submit Leave (VL) | File on behalf (filed_by_emp_id / Group Leader) | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Attachments — store / replace / download | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Overlap validation + activity submitted | Done | 91%
Employee Leave Filing | Submit Leave (VL) | Email notify approvers on submit | Done | 91% | LeaveSubmittedMail
Employee Leave Filing | Submit Leave (VL) | Testing — submit / LWOP / on-behalf cases | Todo | 91%
Employee Leave Filing | My Leaves List | Routes & controller — GET /leaves | Done | 75%
Employee Leave Filing | My Leaves List | Data fetch — paginate for employee | Done | 75%
Employee Leave Filing | My Leaves List | LeaveResource response shape | Done | 75%
Employee Leave Filing | My Leaves List | Testing — list filters & pagination | Todo | 75%
Employee Leave Filing | Modify Leave (while pending) | Routes & controller — PUT/POST /leaves/{id} | Done | 83% | POST preferred for multipart
Employee Leave Filing | Modify Leave (while pending) | Validation — only if no requirement satisfied | Done | 83%
Employee Leave Filing | Modify Leave (while pending) | Release + re-reserve when paid_days changes | Done | 83%
Employee Leave Filing | Modify Leave (while pending) | Activity — modified | Done | 83%
Employee Leave Filing | Modify Leave (while pending) | Block edit after partial approval | Done | 83%
Employee Leave Filing | Modify Leave (while pending) | Testing — edit / blocked-edit cases | Todo | 83%
Employee Leave Filing | Cancel Leave | Routes & controller — POST /leaves/{id}/cancel | Done | 80%
Employee Leave Filing | Cancel Leave | Validation — cancellation_reason required | Done | 80%
Employee Leave Filing | Cancel Leave | Release reserved credits | Done | 80%
Employee Leave Filing | Cancel Leave | Activity — cancelled (no approval_history row) | Done | 80%
Employee Leave Filing | Cancel Leave | Testing — cancel pending / partially approved | Todo | 80%
Approver / PIC | Pending Approvals Dashboard | Routes & controller — GET /approvals/pending | Done | 60%
Approver / PIC | Pending Approvals Dashboard | Data aggregation — formspic group scope | Done | 60%
Approver / PIC | Pending Approvals Dashboard | Response — actionable leaves for approver | Done | 60%
Approver / PIC | Pending Approvals Dashboard | Stakeholder — special group rules (KRM / checkTier) | Todo | 60% | open in APPROVAL_RULES
Approver / PIC | Pending Approvals Dashboard | Testing — visibility by role / group | Todo | 60%
Approver / PIC | Approve / Reject Leave | Routes & controller — approve / reject | Done | 68%
Approver / PIC | Approve / Reject Leave | Approval policy matrix (regular → P4 / president) | Done | 68%
Approver / PIC | Approve / Reject Leave | Approve path — partially_approved → confirmed | Done | 68%
Approver / PIC | Approve / Reject Leave | Reject path — close leave + release reserve | Done | 68%
Approver / PIC | Approve / Reject Leave | First actor wins (UNIQUE requirement_id) | Done | 68%
Approver / PIC | Approve / Reject Leave | Finalize — confirmPaidDays / skip ledger if full LWOP | Done | 68%
Approver / PIC | Approve / Reject Leave | President fallback when no PIC for group | Partial | 68% | config + resolver; verify prod emp ID
Approver / PIC | Approve / Reject Leave | Notify employee on confirm | Done | 68% | LeaveConfirmedMail
Approver / PIC | Approve / Reject Leave | Notify filer / employee on reject | Todo | 68% | not implemented yet
Approver / PIC | Approve / Reject Leave | Notify next-tier approvers after partial approve | Todo | 68% | only first requirement notified on submit
Approver / PIC | Approve / Reject Leave | Testing — matrix, reject, finalize edge cases | Todo | 68%
Balance & Credits | Balance Ledger & Buckets | Routes & controller — GET /balances | Done | 44%
Balance & Credits | Balance Ledger & Buckets | reserve / confirm / releaseReservation | Done | 44%
Balance & Credits | Balance Ledger & Buckets | applyInitialBalance + applyManualAdjustment | Done | 44%
Balance & Credits | Balance Ledger & Buckets | Dev seed — leave:seed-balance | Done | 44%
Balance & Credits | Balance Ledger & Buckets | applyAnnualEntitlement (15/15 or 15/18 by tenure) | Todo | 44% | BALANCE_FLOW.md
Balance & Credits | Balance Ledger & Buckets | applyMonthlyAccrual (+1.25 VL/SL) | Todo | 44%
Balance & Credits | Balance Ledger & Buckets | Scheduled jobs — entitlement / accrual | Todo | 44%
Balance & Credits | Balance Ledger & Buckets | reverseConfirmedLeave (admin undo) | Todo | 44%
Balance & Credits | Balance Ledger & Buckets | Testing — ledger invariants & locking | Todo | 44%
Balance & Credits | Legacy Balance Migration | Document cutover (initial_balance from leave_confirmation) | Done | 33%
Balance & Credits | Legacy Balance Migration | Dev helpers for seeding balances | Done | 33%
Balance & Credits | Legacy Balance Migration | Production migration script | Todo | 33%
Balance & Credits | Legacy Balance Migration | Plan for open pending legacy requests | Todo | 33%
Balance & Credits | Legacy Balance Migration | Guard — skip corrupted negative durations | Todo | 33%
Balance & Credits | Legacy Balance Migration | Testing — migration dry-run / idempotency | Todo | 33%
Admin / Special Flows | VL → SL Conversion | Schema — leave_conversion table + model + enums | Done | 14%
Admin / Special Flows | VL → SL Conversion | Routes — employee request + med cert upload | Todo | 14%
Admin / Special Flows | VL → SL Conversion | Admin review — approve / reject endpoints | Todo | 14%
Admin / Special Flows | VL → SL Conversion | Balance — vl_to_sl_restore + vl_to_sl_deduct | Todo | 14%
Admin / Special Flows | VL → SL Conversion | Activity — conversion_requested / approved / rejected | Todo | 14%
Admin / Special Flows | VL → SL Conversion | leave_info → converted_to_sl + type SL | Todo | 14%
Admin / Special Flows | VL → SL Conversion | Testing — approve / reject / balance side effects | Todo | 14%
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Leave type codes seeded | Done | 20%
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Submit flows beyond VL | Todo | 20%
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Admin requirement rows on original request | Todo | 20%
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Stakeholder — exact requirement sets per type | Todo | 20% | open in APPROVAL_RULES
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Testing — per-type approval paths | Todo | 20%
Admin / Special Flows | Reports & Visibility | Pending approvals scoped to formspic groups | Partial | 10% | pending list exists; full reports no
Admin / Special Flows | Reports & Visibility | Report API — sum confirmed leave_info (not balance) | Todo | 10%
Admin / Special Flows | Reports & Visibility | Quarterly absence warnings (informational) | Todo | 10%
Admin / Special Flows | Reports & Visibility | Stakeholder — report access / special groups | Todo | 10%
Admin / Special Flows | Reports & Visibility | Testing — report totals & access | Todo | 10%
Admin / Special Flows | Notifications (remaining) | Submit notify to approvers | Done | 33% | LeaveNotificationService
Admin / Special Flows | Notifications (remaining) | Confirm notify to employee / filer | Done | 33% | LeaveConfirmedMail
Admin / Special Flows | Notifications (remaining) | Reject notify to employee / filer | Todo | 33%
Admin / Special Flows | Notifications (remaining) | Notify next approvers after partial approve | Todo | 33%
Admin / Special Flows | Notifications (remaining) | Conversion review outcome notify | Todo | 33%
Admin / Special Flows | Notifications (remaining) | Testing — mail / notification payloads | Todo | 33%

## By Module
Leave Forms Revamp — By Module (reference layout)
Overall: 57% · Done 51 · Partial 2 · Todo 38 · Updated 2026-07-22
Schema & Data Model — 100% (5/5)
# | Task | Status
1 | Migrations — 8 revamp tables (leave_type → leave_conversion) | Done
2 | Indexes & unique constraints (SCHEMA.md) | Done
3 | Eloquent models + PHP backed enums | Done
4 | LeaveTypeSeeder (VL, SL, EL, ML, PL, PTB, LL) | Done
5 | kdtphdb read models (employee, formspic, holiday, login) | Done
Portal Auth & Access — 67% (4/6)
# | Task | Status
1 | Dual DB setup — formsdb + kdtphdb (read-only) | Done
2 | Portal cookie auth (userID → kdtlogin) | Done
3 | Routes — GET /api/me, GET /api/health | Done
4 | Config — president_emp_id, CORS, attachments, notifications | Done
5 | Production portal / session cutover with infra | Todo
6 | Testing — auth middleware & health checks | Todo
Submit Leave (VL) — 91% (10/11)
# | Task | Status
1 | Routes & controller — POST /leaves | Done
2 | Validation — StoreLeaveRequest + attachment rules | Done
3 | Duration calc — workdays, holidays, half-day | Done
4 | paid_days / lwop_days split from available | Done
5 | Snapshot approval requirements at submit | Done
6 | Reserve paid credits (leave_reserved) | Done
7 | File on behalf (filed_by_emp_id / Group Leader) | Done
8 | Attachments — store / replace / download | Done
9 | Overlap validation + activity submitted | Done
10 | Email notify approvers on submit | Done
11 | Testing — submit / LWOP / on-behalf cases | Todo
My Leaves List — 75% (3/4)
# | Task | Status
1 | Routes & controller — GET /leaves | Done
2 | Data fetch — paginate for employee | Done
3 | LeaveResource response shape | Done
4 | Testing — list filters & pagination | Todo
Modify Leave (while pending) — 83% (5/6)
# | Task | Status
1 | Routes & controller — PUT/POST /leaves/{id} | Done
2 | Validation — only if no requirement satisfied | Done
3 | Release + re-reserve when paid_days changes | Done
4 | Activity — modified | Done
5 | Block edit after partial approval | Done
6 | Testing — edit / blocked-edit cases | Todo
Cancel Leave — 80% (4/5)
# | Task | Status
1 | Routes & controller — POST /leaves/{id}/cancel | Done
2 | Validation — cancellation_reason required | Done
3 | Release reserved credits | Done
4 | Activity — cancelled (no approval_history row) | Done
5 | Testing — cancel pending / partially approved | Todo
Pending Approvals Dashboard — 60% (3/5)
# | Task | Status
1 | Routes & controller — GET /approvals/pending | Done
2 | Data aggregation — formspic group scope | Done
3 | Response — actionable leaves for approver | Done
4 | Stakeholder — special group rules (KRM / checkTier) | Todo
5 | Testing — visibility by role / group | Todo
Approve / Reject Leave — 68% (7/11)
# | Task | Status
1 | Routes & controller — approve / reject | Done
2 | Approval policy matrix (regular → P4 / president) | Done
3 | Approve path — partially_approved → confirmed | Done
4 | Reject path — close leave + release reserve | Done
5 | First actor wins (UNIQUE requirement_id) | Done
6 | Finalize — confirmPaidDays / skip ledger if full LWOP | Done
7 | President fallback when no PIC for group | Partial
8 | Notify employee on confirm | Done
9 | Notify filer / employee on reject | Todo
10 | Notify next-tier approvers after partial approve | Todo
11 | Testing — matrix, reject, finalize edge cases | Todo
Balance Ledger & Buckets — 44% (4/9)
# | Task | Status
1 | Routes & controller — GET /balances | Done
2 | reserve / confirm / releaseReservation | Done
3 | applyInitialBalance + applyManualAdjustment | Done
4 | Dev seed — leave:seed-balance | Done
5 | applyAnnualEntitlement (15/15 or 15/18 by tenure) | Todo
6 | applyMonthlyAccrual (+1.25 VL/SL) | Todo
7 | Scheduled jobs — entitlement / accrual | Todo
8 | reverseConfirmedLeave (admin undo) | Todo
9 | Testing — ledger invariants & locking | Todo
Legacy Balance Migration — 33% (2/6)
# | Task | Status
1 | Document cutover (initial_balance from leave_confirmation) | Done
2 | Dev helpers for seeding balances | Done
3 | Production migration script | Todo
4 | Plan for open pending legacy requests | Todo
5 | Guard — skip corrupted negative durations | Todo
6 | Testing — migration dry-run / idempotency | Todo
VL → SL Conversion — 14% (1/7)
# | Task | Status
1 | Schema — leave_conversion table + model + enums | Done
2 | Routes — employee request + med cert upload | Todo
3 | Admin review — approve / reject endpoints | Todo
4 | Balance — vl_to_sl_restore + vl_to_sl_deduct | Todo
5 | Activity — conversion_requested / approved / rejected | Todo
6 | leave_info → converted_to_sl + type SL | Todo
7 | Testing — approve / reject / balance side effects | Todo
Other Leave Types (EL, ML, PL, PTB, LL) — 20% (1/5)
# | Task | Status
1 | Leave type codes seeded | Done
2 | Submit flows beyond VL | Todo
3 | Admin requirement rows on original request | Todo
4 | Stakeholder — exact requirement sets per type | Todo
5 | Testing — per-type approval paths | Todo
Reports & Visibility — 10% (0/5)
# | Task | Status
1 | Pending approvals scoped to formspic groups | Partial
2 | Report API — sum confirmed leave_info (not balance) | Todo
3 | Quarterly absence warnings (informational) | Todo
4 | Stakeholder — report access / special groups | Todo
5 | Testing — report totals & access | Todo
Notifications (remaining) — 33% (2/6)
# | Task | Status
1 | Submit notify to approvers | Done
2 | Confirm notify to employee / filer | Done
3 | Reject notify to employee / filer | Todo
4 | Notify next approvers after partial approve | Todo
5 | Conversion review outcome notify | Todo
6 | Testing — mail / notification payloads | Todo

## Legend
Legend & scoring
Status | Meaning | Score toward %
Done | Implemented in the Laravel API | 1
Partial | Started / config present / incomplete | 0.5
Todo | Not started | 0
Section colors
Foundation
Employee Leave Filing
Approver / PIC
Balance & Credits
Admin / Special Flows
Sources
docs/SCHEMA.md, docs/BALANCE_FLOW.md, docs/APPROVAL_RULES.md, docs/LEGACY_NOTES.md
app/Services/Leave/*, routes/api.php, app/Mail/Leave/*, database/migrations
Recent progress since prior checklist: submit + confirm email notifications (LeaveNotificationService, LeaveSubmittedMail, LeaveConfirmedMail)