## Schedule
Tentative Schedule — Backend API development (to end of August 2026)
Dates adjusted to actual progress. Started first week of July (2026-07-01). Weekdays only. Updated 2026-07-22
Phases 2–3 are NOT fully complete: VL path is largely done; other leave types (EL/ML/PL/PTB/LL) still open. Phase 1 done. Phase 4 = main remaining Aug work (conversion, manual balances, reports, non-VL). August = development only through 2026-08-31. Testing & docs from 2026-09-01. Legacy stays separate — no leave history import; opening balances entered manually.
Phase | Start | End | Days (weekdays) | Status | Focus | Notes
Phase 1 — Foundation (development) | 2026-07-01 | 2026-07-10 | 8 | Completed | Portal auth, /me, /health, dual DB, CORS, schema/models, leave config | Started first week of July (2026-07-01). Schema, dual DB, portal cookie auth, models/enums essentially done. Leave type codes seeded (incl. non-VL) but submit flows for them are not Phase 1.
Phase 2 — Employee APIs (development) | 2026-07-07 | 2026-08-13 | 28 | Partial — VL only | VL: submit, list, edit, cancel, attachments, balances read, on-behalf, submit notify. Still open: other leave-type filing (EL/ML/PL/PTB/LL), reject/next-tier notify leftovers | VL employee path largely shipped (Jul 7 + Jul 17). NOT complete for other leave types — only VL submit exists. End date aligned with FE Phase 2 so remaining non-VL filing can land here if prioritized; otherwise carry into Phase 4.
Phase 3 — Approver APIs (development) | 2026-07-07 | 2026-08-21 | 34 | Partial — VL only | VL: pending inbox, approve/reject, finalize/confirm, file-for-member, confirm email. Still open: admin-requirement paths for other types, president verify, special group rules | VL approval path largely shipped (Jul 7 + Jul 21 confirm mail). Other leave types that need admin (or different matrices) are not done. End date aligned with FE Phase 3.
Phase 4 — Admin APIs (development) | 2026-07-22 | 2026-08-28 | 28 | Started / In progress | VL→SL conversion, admin review, manual opening balances/adjust, reports; other leave types + admin requirements if FE needs; finish notify leftovers | Main remaining Aug work. Includes non-VL leave types when prioritized with FE. No legacy leave import — opening balances entered manually.
Phase 5 — Development complete (commitment) | 2026-08-28 | 2026-08-31 | 2 | Planned | Backend API development targeted for completion (August commitment) | End of August = development only — not full prod go-live. Same meaning as FE Phase 5.
After / alongside development (no fixed end dates yet)
Item | Start | End | Days (weekdays) | Status | Notes
Frontend ↔ backend integration (parallel / TBD) | TBD / parallel | TBD | — | Planned | Ongoing with frontend partner — no fixed day count yet. Update when APIs and cookie/session are ready in each env.
Testing (after development) | 2026-09-01 | TBD | — | Planned | Planned to start on/after 2026-09-01. End date TBD. Not part of August commitment.
Documentation (after development) | 2026-09-01 | TBD | — | Planned | Planned to start on/after 2026-09-01. End date TBD. Include manual opening-balance process notes.
August development progress (excludes Testing, Docs, N/A)
Aug-scope % | 68% | 52 done / 2 partial / 24 todo of 78 Aug-scope tasks

## Summary
Leave Forms Revamp — Backend Progress Checklist
Scored against Laravel API · docs/*.md · Updated 2026-07-22 · N/A tasks excluded from %. Testing/docs excluded from August schedule.
Policy: legacy app remains separate; old leaves do not appear in revamp; opening balances are entered manually (no automated leave_confirmation migration).
Overall % (excl. N/A) | 59% | Aug-scope % | 68%
Done | 52 | Partial | 2 | Todo | 36 | N/A 4
Section | Modules | Tasks* | Done | Partial | Todo | Progress %
Foundation | 2 | 11 | 9 | 0 | 2 | 82%
Employee Leave Filing | 4 | 26 | 22 | 0 | 4 | 85%
Approver / PIC | 2 | 16 | 10 | 1 | 5 | 66%
Balance & Credits | 2 | 14 | 7 | 0 | 7 | 50%
Admin / Special Flows | 4 | 23 | 4 | 1 | 18 | 20%
* Tasks exclude N/A from counts/%
Module breakdown
Section | Module | Tasks* | Done | Partial | Todo | Progress %
Foundation | Schema & Data Model | 5 | 5 | 0 | 0 | 100%
Foundation | Portal Auth & Access | 6 | 4 | 0 | 2 | 67%
Employee Leave Filing | Submit Leave (VL) | 11 | 10 | 0 | 1 | 91%
Employee Leave Filing | My Leaves List | 4 | 3 | 0 | 1 | 75%
Employee Leave Filing | Modify Leave (while pending) | 6 | 5 | 0 | 1 | 83%
Employee Leave Filing | Cancel Leave | 5 | 4 | 0 | 1 | 80%
Approver / PIC | Pending Approvals Dashboard | 5 | 3 | 0 | 2 | 60%
Approver / PIC | Approve / Reject Leave | 11 | 7 | 1 | 3 | 68%
Balance & Credits | Balance Ledger & Buckets | 11 | 4 | 0 | 7 | 36%
Balance & Credits | Opening Balances (manual) | 3 | 3 | 0 | 0 | 100%
Admin / Special Flows | VL → SL Conversion | 7 | 1 | 0 | 6 | 14%
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | 5 | 1 | 0 | 4 | 20%
Admin / Special Flows | Reports & Visibility | 5 | 0 | 1 | 4 | 10%
Admin / Special Flows | Notifications (remaining) | 6 | 2 | 0 | 4 | 33%
Suggested next priorities (Phase 4 — now through Aug 28)
1. Finish VL leftovers: reject email + next-tier approver notify
2. Admin/HR APIs for manual opening balance + adjust (no legacy leave import)
3. VL → SL conversion request/review + balance side effects (FE Phase 4)
4. Other leave types (EL/ML/PL/PTB/LL) submit + admin requirements — Phase 2/3 not done without these
5. Report API (confirmed leave_info only) + staging cookie/env verify with infra

## Checklist
Leave Forms Revamp — Module / Task Checklist (Backend)
Updated 2026-07-22 · Status: Done / Partial / Todo / N/A · Phase = schedule phase · Aug scope = yes/no for August development commitment
Section | Module | Task | Status | Module % | Phase | Aug scope | Notes
Foundation | Schema & Data Model | Migrations — 8 revamp tables (leave_type → leave_conversion) | Done | 100% | 1 | Yes | migrations present
Foundation | Schema & Data Model | Indexes & unique constraints (SCHEMA.md) | Done | 100% | 1 | Yes
Foundation | Schema & Data Model | Eloquent models + PHP backed enums | Done | 100% | 1 | Yes
Foundation | Schema & Data Model | LeaveTypeSeeder (VL, SL, EL, ML, PL, PTB, LL) | Done | 100% | 1 | Yes
Foundation | Schema & Data Model | kdtphdb read models (employee, formspic, holiday, login) | Done | 100% | 1 | Yes
Foundation | Portal Auth & Access | Dual DB setup — formsdb + kdtphdb (read-only) | Done | 67% | 1 | Yes
Foundation | Portal Auth & Access | Portal cookie auth (userID → kdtlogin) | Done | 67% | 1 | Yes
Foundation | Portal Auth & Access | Routes — GET /api/me, GET /api/health | Done | 67% | 1 | Yes
Foundation | Portal Auth & Access | Config — president_emp_id, CORS, attachments, notifications | Done | 67% | 1 | Yes
Foundation | Portal Auth & Access | Staging/prod portal cookie & env verify with infra | Todo | 67% | 1 | Yes | integration / infra — not legacy leave import
Foundation | Portal Auth & Access | Testing — auth middleware & health checks | Todo | 67% | Post-Aug | No | after Aug development
Employee Leave Filing | Submit Leave (VL) | Routes & controller — POST /leaves | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Validation — StoreLeaveRequest + attachment rules | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Duration calc — workdays, holidays, half-day | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | paid_days / lwop_days split from available | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Snapshot approval requirements at submit | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Reserve paid credits (leave_reserved) | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | File on behalf (filed_by_emp_id / Group Leader) | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Attachments — store / replace / download | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Overlap validation + activity submitted | Done | 91% | 2 | Yes
Employee Leave Filing | Submit Leave (VL) | Email notify approvers on submit | Done | 91% | 2 | Yes | LeaveSubmittedMail
Employee Leave Filing | Submit Leave (VL) | Testing — submit / LWOP / on-behalf cases | Todo | 91% | Post-Aug | No | after Aug development
Employee Leave Filing | My Leaves List | Routes & controller — GET /leaves | Done | 75% | 2 | Yes
Employee Leave Filing | My Leaves List | Data fetch — paginate for employee | Done | 75% | 2 | Yes
Employee Leave Filing | My Leaves List | LeaveResource response shape | Done | 75% | 2 | Yes
Employee Leave Filing | My Leaves List | Testing — list filters & pagination | Todo | 75% | Post-Aug | No | after Aug development
Employee Leave Filing | Modify Leave (while pending) | Routes & controller — PUT/POST /leaves/{id} | Done | 83% | 2 | Yes | POST preferred for multipart
Employee Leave Filing | Modify Leave (while pending) | Validation — only if no requirement satisfied | Done | 83% | 2 | Yes
Employee Leave Filing | Modify Leave (while pending) | Release + re-reserve when paid_days changes | Done | 83% | 2 | Yes
Employee Leave Filing | Modify Leave (while pending) | Activity — modified | Done | 83% | 2 | Yes
Employee Leave Filing | Modify Leave (while pending) | Block edit after partial approval | Done | 83% | 2 | Yes
Employee Leave Filing | Modify Leave (while pending) | Testing — edit / blocked-edit cases | Todo | 83% | Post-Aug | No | after Aug development
Employee Leave Filing | Cancel Leave | Routes & controller — POST /leaves/{id}/cancel | Done | 80% | 2 | Yes
Employee Leave Filing | Cancel Leave | Validation — cancellation_reason required | Done | 80% | 2 | Yes
Employee Leave Filing | Cancel Leave | Release reserved credits | Done | 80% | 2 | Yes
Employee Leave Filing | Cancel Leave | Activity — cancelled (no approval_history row) | Done | 80% | 2 | Yes
Employee Leave Filing | Cancel Leave | Testing — cancel pending / partially approved | Todo | 80% | Post-Aug | No | after Aug development
Approver / PIC | Pending Approvals Dashboard | Routes & controller — GET /approvals/pending | Done | 60% | 3 | Yes
Approver / PIC | Pending Approvals Dashboard | Data aggregation — formspic group scope | Done | 60% | 3 | Yes
Approver / PIC | Pending Approvals Dashboard | Response — actionable leaves for approver | Done | 60% | 3 | Yes
Approver / PIC | Pending Approvals Dashboard | Stakeholder — special group rules (KRM / checkTier) | Todo | 60% | 3 | Yes | only if FE inbox needs it in Aug
Approver / PIC | Pending Approvals Dashboard | Testing — visibility by role / group | Todo | 60% | Post-Aug | No | after Aug development
Approver / PIC | Approve / Reject Leave | Routes & controller — approve / reject | Done | 68% | 3 | Yes
Approver / PIC | Approve / Reject Leave | Approval policy matrix (regular → P4 / president) | Done | 68% | 3 | Yes
Approver / PIC | Approve / Reject Leave | Approve path — partially_approved → confirmed | Done | 68% | 3 | Yes
Approver / PIC | Approve / Reject Leave | Reject path — close leave + release reserve | Done | 68% | 3 | Yes
Approver / PIC | Approve / Reject Leave | First actor wins (UNIQUE requirement_id) | Done | 68% | 3 | Yes
Approver / PIC | Approve / Reject Leave | Finalize — confirmPaidDays / skip ledger if full LWOP | Done | 68% | 3 | Yes
Approver / PIC | Approve / Reject Leave | President fallback when no PIC for group | Partial | 68% | 3 | Yes | config + resolver; verify staging emp ID
Approver / PIC | Approve / Reject Leave | Notify employee on confirm | Done | 68% | 3 | Yes | LeaveConfirmedMail
Approver / PIC | Approve / Reject Leave | Notify filer / employee on reject | Todo | 68% | 2 | Yes
Approver / PIC | Approve / Reject Leave | Notify next-tier approvers after partial approve | Todo | 68% | 2 | Yes
Approver / PIC | Approve / Reject Leave | Testing — matrix, reject, finalize edge cases | Todo | 68% | Post-Aug | No | after Aug development
Balance & Credits | Balance Ledger & Buckets | Routes & controller — GET /balances | Done | 36% | 2 | Yes
Balance & Credits | Balance Ledger & Buckets | reserve / confirm / releaseReservation | Done | 36% | 2 | Yes
Balance & Credits | Balance Ledger & Buckets | applyInitialBalance + applyManualAdjustment | Done | 36% | 4 | Yes | service methods exist
Balance & Credits | Balance Ledger & Buckets | Dev seed — leave:seed-balance | Done | 36% | 1 | Yes | local only
Balance & Credits | Balance Ledger & Buckets | Admin/HR API — set opening balance (manual from legacy) | Todo | 36% | 4 | Yes | manual entry; no bulk legacy import
Balance & Credits | Balance Ledger & Buckets | Admin/HR API — manual adjust with remarks | Todo | 36% | 4 | Yes | expose applyManualAdjustment
Balance & Credits | Balance Ledger & Buckets | applyAnnualEntitlement (15/15 or 15/18 by tenure) | Todo | 36% | 4 | Yes | if needed for Aug admin/FE
Balance & Credits | Balance Ledger & Buckets | applyMonthlyAccrual (+1.25 VL/SL) | Todo | 36% | 4 | Yes | if needed for Aug admin/FE
Balance & Credits | Balance Ledger & Buckets | Scheduled jobs — entitlement / accrual | Todo | 36% | 4 | Yes | can slip past Aug if manual grant OK
Balance & Credits | Balance Ledger & Buckets | reverseConfirmedLeave (admin undo) | Todo | 36% | 4 | Yes
Balance & Credits | Balance Ledger & Buckets | Testing — ledger invariants & locking | Todo | 36% | Post-Aug | No | after Aug development
Balance & Credits | Opening Balances (manual) | Decision — legacy and revamp stay separate apps | Done | 100% | 4 | Yes | no shared leave history
Balance & Credits | Opening Balances (manual) | Decision — old leaves do NOT appear in revamp | Done | 100% | 4 | Yes | revamp starts clean
Balance & Credits | Opening Balances (manual) | Decision — opening credits entered manually from legacy | Done | 100% | 4 | Yes | HR keys available VL/SL etc.
Balance & Credits | Opening Balances (manual) | Bulk leave_confirmation → leave_balance migration script | N/A | 100% | — | No | not using automated data migration
Balance & Credits | Opening Balances (manual) | Import / carry over open pending legacy leave requests | N/A | 100% | — | No | employees re-file in revamp if needed
Balance & Credits | Opening Balances (manual) | Guard — skip corrupted negative legacy durations | N/A | 100% | — | No | no legacy leave import
Balance & Credits | Opening Balances (manual) | Testing — migration dry-run / idempotency | N/A | 100% | — | No | no migration script
Admin / Special Flows | VL → SL Conversion | Schema — leave_conversion table + model + enums | Done | 14% | 4 | Yes
Admin / Special Flows | VL → SL Conversion | Routes — employee request + med cert upload | Todo | 14% | 4 | Yes | aligns with FE admin conversion
Admin / Special Flows | VL → SL Conversion | Admin review — approve / reject endpoints | Todo | 14% | 4 | Yes
Admin / Special Flows | VL → SL Conversion | Balance — vl_to_sl_restore + vl_to_sl_deduct | Todo | 14% | 4 | Yes
Admin / Special Flows | VL → SL Conversion | Activity — conversion_requested / approved / rejected | Todo | 14% | 4 | Yes
Admin / Special Flows | VL → SL Conversion | leave_info → converted_to_sl + type SL | Todo | 14% | 4 | Yes
Admin / Special Flows | VL → SL Conversion | Testing — approve / reject / balance side effects | Todo | 14% | Post-Aug | No | after Aug development
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Leave type codes seeded | Done | 20% | 4 | Yes
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Submit flows beyond VL | Todo | 20% | 4 | Yes | if FE needs in Aug Phase 4
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Admin requirement rows on original request | Todo | 20% | 4 | Yes
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Stakeholder — exact requirement sets per type | Todo | 20% | 4 | Yes | open in APPROVAL_RULES
Admin / Special Flows | Other Leave Types (EL, ML, PL, PTB, LL) | Testing — per-type approval paths | Todo | 20% | Post-Aug | No | after Aug development
Admin / Special Flows | Reports & Visibility | Pending approvals scoped to formspic groups | Partial | 10% | 4 | Yes | pending list exists; full reports no
Admin / Special Flows | Reports & Visibility | Report API — sum confirmed leave_info (not balance) | Todo | 10% | 4 | Yes | revamp leaves only
Admin / Special Flows | Reports & Visibility | Quarterly absence warnings (informational) | Todo | 10% | 4 | Yes
Admin / Special Flows | Reports & Visibility | Stakeholder — report access / special groups | Todo | 10% | 4 | Yes
Admin / Special Flows | Reports & Visibility | Testing — report totals & access | Todo | 10% | Post-Aug | No | after Aug development
Admin / Special Flows | Notifications (remaining) | Submit notify to approvers | Done | 33% | 2 | Yes | LeaveNotificationService
Admin / Special Flows | Notifications (remaining) | Confirm notify to employee / filer | Done | 33% | 3 | Yes | LeaveConfirmedMail
Admin / Special Flows | Notifications (remaining) | Reject notify to employee / filer | Todo | 33% | 2 | Yes
Admin / Special Flows | Notifications (remaining) | Notify next approvers after partial approve | Todo | 33% | 2 | Yes
Admin / Special Flows | Notifications (remaining) | Conversion review outcome notify | Todo | 33% | 4 | Yes
Admin / Special Flows | Notifications (remaining) | Testing — mail / notification payloads | Todo | 33% | Post-Aug | No | after Aug development

## By Module
Leave Forms Revamp — By Module (Backend)
Overall (excl. N/A): 59% · Aug-scope: 68% · Done 52 · Partial 2 · Todo 36 · N/A 4 · Updated 2026-07-22
Schema & Data Model — 100% (5/5 active)
# | Task | Status | Aug scope
1 | Migrations — 8 revamp tables (leave_type → leave_conversion) | Done | Yes
2 | Indexes & unique constraints (SCHEMA.md) | Done | Yes
3 | Eloquent models + PHP backed enums | Done | Yes
4 | LeaveTypeSeeder (VL, SL, EL, ML, PL, PTB, LL) | Done | Yes
5 | kdtphdb read models (employee, formspic, holiday, login) | Done | Yes
Portal Auth & Access — 67% (4/6 active)
# | Task | Status | Aug scope
1 | Dual DB setup — formsdb + kdtphdb (read-only) | Done | Yes
2 | Portal cookie auth (userID → kdtlogin) | Done | Yes
3 | Routes — GET /api/me, GET /api/health | Done | Yes
4 | Config — president_emp_id, CORS, attachments, notifications | Done | Yes
5 | Staging/prod portal cookie & env verify with infra | Todo | Yes
6 | Testing — auth middleware & health checks | Todo | No
Submit Leave (VL) — 91% (10/11 active)
# | Task | Status | Aug scope
1 | Routes & controller — POST /leaves | Done | Yes
2 | Validation — StoreLeaveRequest + attachment rules | Done | Yes
3 | Duration calc — workdays, holidays, half-day | Done | Yes
4 | paid_days / lwop_days split from available | Done | Yes
5 | Snapshot approval requirements at submit | Done | Yes
6 | Reserve paid credits (leave_reserved) | Done | Yes
7 | File on behalf (filed_by_emp_id / Group Leader) | Done | Yes
8 | Attachments — store / replace / download | Done | Yes
9 | Overlap validation + activity submitted | Done | Yes
10 | Email notify approvers on submit | Done | Yes
11 | Testing — submit / LWOP / on-behalf cases | Todo | No
My Leaves List — 75% (3/4 active)
# | Task | Status | Aug scope
1 | Routes & controller — GET /leaves | Done | Yes
2 | Data fetch — paginate for employee | Done | Yes
3 | LeaveResource response shape | Done | Yes
4 | Testing — list filters & pagination | Todo | No
Modify Leave (while pending) — 83% (5/6 active)
# | Task | Status | Aug scope
1 | Routes & controller — PUT/POST /leaves/{id} | Done | Yes
2 | Validation — only if no requirement satisfied | Done | Yes
3 | Release + re-reserve when paid_days changes | Done | Yes
4 | Activity — modified | Done | Yes
5 | Block edit after partial approval | Done | Yes
6 | Testing — edit / blocked-edit cases | Todo | No
Cancel Leave — 80% (4/5 active)
# | Task | Status | Aug scope
1 | Routes & controller — POST /leaves/{id}/cancel | Done | Yes
2 | Validation — cancellation_reason required | Done | Yes
3 | Release reserved credits | Done | Yes
4 | Activity — cancelled (no approval_history row) | Done | Yes
5 | Testing — cancel pending / partially approved | Todo | No
Pending Approvals Dashboard — 60% (3/5 active)
# | Task | Status | Aug scope
1 | Routes & controller — GET /approvals/pending | Done | Yes
2 | Data aggregation — formspic group scope | Done | Yes
3 | Response — actionable leaves for approver | Done | Yes
4 | Stakeholder — special group rules (KRM / checkTier) | Todo | Yes
5 | Testing — visibility by role / group | Todo | No
Approve / Reject Leave — 68% (7/11 active)
# | Task | Status | Aug scope
1 | Routes & controller — approve / reject | Done | Yes
2 | Approval policy matrix (regular → P4 / president) | Done | Yes
3 | Approve path — partially_approved → confirmed | Done | Yes
4 | Reject path — close leave + release reserve | Done | Yes
5 | First actor wins (UNIQUE requirement_id) | Done | Yes
6 | Finalize — confirmPaidDays / skip ledger if full LWOP | Done | Yes
7 | President fallback when no PIC for group | Partial | Yes
8 | Notify employee on confirm | Done | Yes
9 | Notify filer / employee on reject | Todo | Yes
10 | Notify next-tier approvers after partial approve | Todo | Yes
11 | Testing — matrix, reject, finalize edge cases | Todo | No
Balance Ledger & Buckets — 36% (4/11 active)
# | Task | Status | Aug scope
1 | Routes & controller — GET /balances | Done | Yes
2 | reserve / confirm / releaseReservation | Done | Yes
3 | applyInitialBalance + applyManualAdjustment | Done | Yes
4 | Dev seed — leave:seed-balance | Done | Yes
5 | Admin/HR API — set opening balance (manual from legacy) | Todo | Yes
6 | Admin/HR API — manual adjust with remarks | Todo | Yes
7 | applyAnnualEntitlement (15/15 or 15/18 by tenure) | Todo | Yes
8 | applyMonthlyAccrual (+1.25 VL/SL) | Todo | Yes
9 | Scheduled jobs — entitlement / accrual | Todo | Yes
10 | reverseConfirmedLeave (admin undo) | Todo | Yes
11 | Testing — ledger invariants & locking | Todo | No
Opening Balances (manual) — 100% (3/3 active)
# | Task | Status | Aug scope
1 | Decision — legacy and revamp stay separate apps | Done | Yes
2 | Decision — old leaves do NOT appear in revamp | Done | Yes
3 | Decision — opening credits entered manually from legacy | Done | Yes
4 | Bulk leave_confirmation → leave_balance migration script | N/A | No
5 | Import / carry over open pending legacy leave requests | N/A | No
6 | Guard — skip corrupted negative legacy durations | N/A | No
7 | Testing — migration dry-run / idempotency | N/A | No
VL → SL Conversion — 14% (1/7 active)
# | Task | Status | Aug scope
1 | Schema — leave_conversion table + model + enums | Done | Yes
2 | Routes — employee request + med cert upload | Todo | Yes
3 | Admin review — approve / reject endpoints | Todo | Yes
4 | Balance — vl_to_sl_restore + vl_to_sl_deduct | Todo | Yes
5 | Activity — conversion_requested / approved / rejected | Todo | Yes
6 | leave_info → converted_to_sl + type SL | Todo | Yes
7 | Testing — approve / reject / balance side effects | Todo | No
Other Leave Types (EL, ML, PL, PTB, LL) — 20% (1/5 active)
# | Task | Status | Aug scope
1 | Leave type codes seeded | Done | Yes
2 | Submit flows beyond VL | Todo | Yes
3 | Admin requirement rows on original request | Todo | Yes
4 | Stakeholder — exact requirement sets per type | Todo | Yes
5 | Testing — per-type approval paths | Todo | No
Reports & Visibility — 10% (0/5 active)
# | Task | Status | Aug scope
1 | Pending approvals scoped to formspic groups | Partial | Yes
2 | Report API — sum confirmed leave_info (not balance) | Todo | Yes
3 | Quarterly absence warnings (informational) | Todo | Yes
4 | Stakeholder — report access / special groups | Todo | Yes
5 | Testing — report totals & access | Todo | No
Notifications (remaining) — 33% (2/6 active)
# | Task | Status | Aug scope
1 | Submit notify to approvers | Done | Yes
2 | Confirm notify to employee / filer | Done | Yes
3 | Reject notify to employee / filer | Todo | Yes
4 | Notify next approvers after partial approve | Todo | Yes
5 | Conversion review outcome notify | Todo | Yes
6 | Testing — mail / notification payloads | Todo | No

## Legend
Legend, scoring & cutover policy
Status | Meaning | Score toward %
Done | Implemented in the Laravel API | 1
Partial | Started / config present / incomplete | 0.5
Todo | Not started | 0
N/A | Out of scope by decision (excluded from %) | —
Cutover policy (confirmed)
1. Legacy leaveforms and revamp stay separate.
2. Old leaves do NOT appear in the revamp (no leave history import).
3. Opening balances are entered manually from legacy numbers into revamp.
4. Automated leave_confirmation bulk migration is N/A.
Schedule alignment
Backend started first week of July (2026-07-01), ahead of FE Phase 1 start (2026-07-21).
Phases 2–3 = Partial (VL only). Other leave types (EL/ML/PL/PTB/LL) still todo.
Phase 4 (2026-07-22 → 2026-08-28) covers conversion, manual balances, reports, and non-VL filing as needed.
Testing & Documentation start on/after 2026-09-01 (not August commitment).
FE ↔ BE integration is parallel / TBD.
Sources
docs/SCHEMA.md, BALANCE_FLOW.md, APPROVAL_RULES.md, LEGACY_NOTES.md
app/Services/Leave/*, routes/api.php, app/Mail/Leave/* · git commits 2026-07-07 / 07-17 / 07-21
Frontend schedule reference: Tentative Schedule — Frontend development (to end of August 2026)