## Frontend Tentative Schedule
Tentative Schedule — Frontend development (to end of August 2026)
Started 2026-07-21. August commitment = DEVELOPMENT only (through 2026-08-31). Backend integration dates TBD. Testing & documentation after development.
Phase | Start Date | End Date | Days (weekdays) | Focus | Weekly Date
Phase 1 — Foundation (development) | 2026-07-21 | 2026-07-30 |  | Project setup, layout, menus, reusable UI.
Phase 2 — Employee features (development) | 2026-07-28 | 2026-08-13 |  | Dashboard, file leave, request details, history, edit, and cancel.
Phase 3 — Approver / team (development) | 2026-08-11 | 2026-08-21 |  | Approvals inbox, approve/reject, file for member, team calendar.
Phase 4 — Admin features (development) | 2026-08-18 | 2026-08-28 |  | Admin requests, conversion review, balances, logs, and reports.
Phase 5 — Development complete (commitment) | 2026-08-28 | 2026-08-31 |  | Frontend development screens targeted complete. End of August = development only.
After / alongside development (no fixed end dates yet)
Item | Notes
Backend integration (parallel / TBD) | Ongoing with backend partner — no fixed day count yet. Update when APIs and cookie/session are ready.
Testing (after development) | Planned to start on/after 2026-09-01. End date TBD.
Documentation (after development) | Planned to start on/after 2026-09-01. End date TBD.
Overall % |  | Completed |  | In Progress |  | Not Started
Section | Tasks | Completed | In Progress | Not Started | Blocked | Progress %
1. Project Setup
2. Core App Shell
3. Employee Features
4. Approver / Team Features
5. Admin Features
6. Backend Integration (TBD)
7. Testing (after development)
8. Documentation (after development)
Formulas:
Days (weekdays) = NETWORKDAYS([Start Date],[End Date])

## Backend Tentative Schedule
Tentative Schedule — Backend development (to end of August 2026)
Started first week of July. August commitment = DEVELOPMENT only (through 2026-08-31). Frontend integration TBD. Testing & documentation after development. Progress % below uses Backend Progress Tracker (same scoring as Frontend).
Phase | Start Date | Target End Date | Days (weekdays) | Focus | Weekly Date
Phase 1 — Foundation (development) | 2026-07-06 | 2026-07-17 |  | Portal auth, /me, /health, dual DB, CORS, schema/models, leave config
Phase 2 — Employee features (development) | 2026-07-20 | 2026-08-14 |  | VL: submit, list, edit, cancel, attachments, balances read, on-behalf, submit notify. Still open: other leave-type filing (EL/ML/PL/PTB/LL), reject/next-tier notify leftovers
Phase 3 — Approver APIs (development) | 2026-07-24 | 2026-08-14 |  | VL: pending inbox, approve/reject, finalize/confirm, file-for-member, confirm email. Still open: admin-requirement paths for other types, president verify, special group rules
Phase 4 — Admin APIs (development) | 2026-08-18 | 2026-08-28 |  | VL→SL conversion, admin review, manual opening balances/adjust, reports; other leave types + admin requirements if FE needs; finish notify leftovers
Phase 5 — Development complete (commitment) | 2026-08-28 | 2026-08-31 |  | Backend API development targeted for completion (August commitment)
After / alongside development (no fixed end dates yet)
Item | Notes
Frontend integration (parallel / TBD) | Ongoing with frontend partner — no fixed day count yet. Update when frontend pages are ready.
Testing (after development) | Planned to start on/after 2026-09-01. End date TBD.
Documentation (after development) | Planned to start on/after 2026-09-01. End date TBD.
Overall % |  | Completed |  | In Progress |  | Not Started
Section | Tasks | Completed | In Progress | Not Started | Blocked | Progress %
1. Foundation
2. Employee Features
3. Approver Features
4. Admin Features
5. Frontend Integration (TBD)
6. Testing (after development)
7. Documentation (after development)
Formulas:
Days (weekdays) = NETWORKDAYS([Start Date],[Target End Date])

## Backend Progress Tracker
Section | Task | Status | Progress %
1. Foundation | Dual DB setup — formsdb + kdtphdb (read-only) | Completed
1. Foundation | Portal cookie auth (userID → kdtlogin) | Completed
1. Foundation | Routes — GET /api/me, GET /api/health | Completed
1. Foundation | Schema migrations — 8 revamp tables + indexes | Completed
1. Foundation | Eloquent models + PHP backed enums | Completed
1. Foundation | LeaveTypeSeeder (VL, SL, EL, ML, PL, PTB, LL) | Completed
1. Foundation | Config — president_emp_id, CORS, attachments, notifications | Completed
1. Foundation | Staging/prod portal cookie & env verify with infra | In Progress
2. Employee Features | POST /leaves — submit VL with validation | Completed
2. Employee Features | Duration calc — workdays, holidays, half-day | Completed
2. Employee Features | paid_days / lwop_days split + reserve credits | Completed
2. Employee Features | Snapshot approval requirements at submit | Completed
2. Employee Features | File on behalf (filed_by_emp_id / Group Leader) | Completed
2. Employee Features | Attachments — store / replace / download | Completed
2. Employee Features | GET /leaves — list / LeaveResource | Completed
2. Employee Features | PUT/POST /leaves/{id} — modify while pending | Completed
2. Employee Features | POST /leaves/{id}/cancel | Completed
2. Employee Features | GET /balances — read leave credits | Completed
2. Employee Features | Email notify approvers on submit | Completed
2. Employee Features | Reject notify to employee / filer | Not Started
2. Employee Features | Notify next-tier approvers after partial approve | Not Started
2. Employee Features | Submit flows for other leave types (EL/ML/PL/PTB/LL) | Not Started
3. Approver Features | GET /approvals/pending — formspic group scope | Completed
3. Approver Features | Approve path — partially_approved → confirmed | Completed
3. Approver Features | Reject path — close leave + release reserve | Completed
3. Approver Features | Approval policy matrix (regular → P4 / president) | Completed
3. Approver Features | Finalize — confirmPaidDays / skip ledger if full LWOP | Completed
3. Approver Features | Notify employee on confirm | Completed
3. Approver Features | President fallback verify (staging emp ID) | In Progress
3. Approver Features | Stakeholder — special group rules (KRM / checkTier) | Not Started
3. Approver Features | Admin-requirement approval paths for other leave types | Not Started
4. Admin Features | leave_conversion schema + model + enums | Completed
4. Admin Features | Opening balances policy — manual entry (no legacy leave import) | Completed
4. Admin Features | applyInitialBalance + applyManualAdjustment (service) | Completed
4. Admin Features | Admin/HR API — set opening balance (manual from legacy) | Not Started
4. Admin Features | Admin/HR API — manual adjust with remarks | Not Started
4. Admin Features | VL → SL conversion request + med cert upload | Not Started
4. Admin Features | Admin conversion review — approve / reject | Not Started
4. Admin Features | Conversion balance — vl_to_sl_restore + deduct | Not Started
4. Admin Features | Conversion notify outcome | Not Started
4. Admin Features | applyAnnualEntitlement / monthly accrual / jobs | Not Started
4. Admin Features | reverseConfirmedLeave (admin undo) | Not Started
4. Admin Features | Report API — sum confirmed leave_info | Not Started
4. Admin Features | Quarterly absence warnings | Not Started
4. Admin Features | Other leave types — admin requirement rows + stakeholder sets | Not Started
5. Frontend Integration (TBD) | Wire FE screens to real API routes | In Progress
5. Frontend Integration (TBD) | Portal cookie / CORS / env per environment | In Progress
5. Frontend Integration (TBD) | Contract alignment — LeaveResource / balances payloads | In Progress
5. Frontend Integration (TBD) | End-to-end smoke: submit → approve → confirm | Not Started
6. Testing (after development) | Feature tests — submit / approve / reject / cancel | Not Started
6. Testing (after development) | Balance ledger invariant tests | Not Started
6. Testing (after development) | Approval policy matrix tests | Not Started
6. Testing (after development) | Conversion + notification tests | Not Started
7. Documentation (after development) | API endpoint notes for FE partner | Not Started
7. Documentation (after development) | Manual opening-balance process notes for HR | Not Started
7. Documentation (after development) | Env / portal cookie cutover checklist | Not Started
Commitment: backend DEVELOPMENT by end of August (weekdays). Phases 2–3 are Partial (VL only) until other leave types are done. Testing & Documentation after development (from Sep 2026). Legacy leaves stay in legacy app; opening balances entered manually. Change Status in column C — Progress % and the Backend Tentative Schedule summary update automatically.